## Sheet1
| Project Start Date | 2024-05-13 |  |  |  |  | 2024 |  |  | 2024 |  |  |  | 2024 |  |  |  |  | 2024 |  |  |  | 2024
[7 empty] | MAY |  |  | JUN |  |  |  | JUL |  |  |  |  | AUG |  |  |  | SEP
| Project Name | Detecting Automatically Generated User comments Using Language-models |  |  |  | Week Starting | 2024-05-13 | 2024-05-20 | 2024-05-27 | 2024-06-03 | 2024-06-10 | 2024-06-17 | 2024-06-24 | 2024-07-01 | 2024-07-08 | 2024-07-15 | 2024-07-22 | 2024-07-29 | 2024-08-05 | 2024-08-12 | 2024-08-19 | 2024-08-26 | 2024-09-02 | 2024-09-09 | 2024-09-16 | 2024-09-23 | 2024-09-30 | [12 empty] | 1900-01-06
# | Milestone | Start date | End Date | Days | Status | % Done
| Kick-off Meeting | 2024-05-13 | 2024-05-13 |  | Completed | 100% | bar: 2024-05-13
| Workshop 1: How to Prepare Project Proposal | 2024-05-13 | 2024-05-13 | 1 | Completed | 100% | bar: 2024-05-20
| Project Start | 2024-05-20 | 2024-05-20 | 1 | Completed | 100% | bar: 2024-05-20
| Supervisor Assignment | 2024-05-20 | 2024-05-20 | 1 | Completed | 100% | bar: 2024-06-03
| Proposal Submission | 2024-06-03 | 2024-06-07 | 4 | Completed | 100% | bar: 2024-07-08
| Workshop 2: Literature Review and Critical Thinking | 2024-07-10 | 2024-07-10 | 1 | Completed | 100% | bar: 2024-07-22
| Mid-Point Review | 2024-07-22 | 2024-07-22 | 1 | Completed | 100% | bar: 2024-07-15
| Data Collection | 2024-07-11 | 2024-07-16 | 5 | Completed | 100% | bar: 2024-07-15
| Data Preprocessing | 2024-07-17 | 2024-07-17 | 1 | Completed | 100% | bar: 2024-07-22
| Model Development | 2024-07-17 | 2024-07-23 | 6 | Completed | 100% | bar: 2024-07-22
| Initial Model Training | 2024-07-23 | 2024-07-24 | 2 | Completed | 100% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Model Evaluation and Testing | 2024-07-24 | 1-Agu-24 | 7 | Completed | 100% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Model Refinement | 2-Agu-24 | 3-Agu-24 | 2 | Completed | 100%
| Draft report submission | 2024-08-12 |  |  | Completed | 100%
| Project Final Submission | 2024-08-27 |  |  | In progress | 90%
| Vivas and Marking | 2024-09-01
Project End
Statuses
Not Started
In progress
Blocked
Completed

## Sheet2
Detailed Project Development Gantt Chart
START DATE | END DATE | MILESTONE | POSITION 1 | POSITION 2 | POSITION 3 | NOTES
2024-05-13 | 2024-05-13 | Kick-off Meeting | 25 | 0 | 25 | Initial meeting to start the project
2024-05-13 | 2024-05-13 | Workshop 1: How to Prepare Project Proposal | 10 | 0 | -10 | Training on proposal preparation
2024-05-20 | 2024-05-20 | Project Start | -10 | 0 | 10 | Official start of the project
2024-05-20 | 2024-05-20 | Supervisor Assignment | 15 | 0 | 15 | Assigning project supervisors
2024-05-21 | 2024-05-30 | Literature Review Start | -15 | 0 | -15 | Begin research and literature review
2024-06-03 | 2024-06-07 | Proposal Submission | 15 | 0 | 15 | Start and end of proposal submission period
2024-06-10 | 2024-06-10 | Workshop 2: Literature Review and Critical Thinking | 15 | 0 | 15 | Workshop on critical thinking and literature
2024-06-15 | 2024-07-15 | Data Collection | -20 | 0 | -20 | Collecting data for LLM fine tuning
2024-07-16 | 2024-07-31 | Data Preprocessing | 15 | 0 | 15 | Preprocessing collected data
2024-08-01 | 2024-08-15 | Model Development | -15 | 0 | -15 | Developing the fine-tuned LLM
2024-08-15 | 2024-08-30 | Initial Model Training | 15 | 0 | 15 | Training the model
2024-09-01 | 2024-09-15 | Model Evaluation and Testing | -20 | 0 | -20 | Evaluating and testing the model
2024-09-16 | 2024-09-16 | Mid-Point Review | 15 | 0 | 15 | Review progress and make adjustments
2024-09-17 | 2024-09-30 | Model Refinement | -20 | 0 | -20 | Refining the model based on feedback
2024-10-01 | 2024-10-15 | Integration with Music Application | 15 | 0 | 15 | Integrate model with application
2024-10-16 | 2024-10-30 | User Testing and Feedback | -20 | 0 | -20 | User testing
2024-11-01 | 2024-11-15 | Final Adjustments | 15 | 0 | 15 | Final adjustments based on feedback
2024-11-16 | 2024-11-30 | Documentation and Reporting | -20 | 0 | -20 | Preparing final documentation
2024-08-26 | 2024-08-26 | Project Final Submission | 15 | 0 | 15 | Submit final project
2024-09-01 | 2024-09-30 | Vivas and Marking | -15 | 0 | -15 | Viva and marking period
2024-12-31 | 2024-12-31 | Project End | 15 | 0 | 15 | Official end of the project